I

TMG REPORT

Document code: TM-CTU-003 Section : CTU

Version: 4.0

ucru

Effective: 06JAN22

43EN: UPDATE REPORT

Reporting Date: Dec 1st, 2025

1. Outstanding Action Points

2. General Trial Procedures

3. Ethics & Regulatory

List details of submissions/amendments:

4. Screening and Recruitment

- From 1st July 2025, started protocol version 2.0.

- Target recruitment: 750 patients and 1-3 close contact/patient from 3 hospital sites.

- Cumulative recruited Patients: 126 patients (17% total target)

- Cumulative recruited Close Contacts: 67 contacts

Page 1 of 5

TM-CTU-003 TEMPLATE TMG REPORT V4.06JAN22

Note: This is a controlled document

- Project agreement: HTD, Cho Ray Hospital

Trang, Thi, Tam

Ongoing

□

| Action Point |  | Actioned by |  | Complete? |  |
| --- | --- | --- | --- | --- | --- |

| Event |  |  |  |  |  |  | Version |  | Date |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Initial approval by Hospital for Tropical Diseases |  |  |  |  |  |  | V1.0 |  | 24th May 2024 |  |  |  |  |
| Initial approval by OxTREC 522-24 |  |  |  |  |  |  | V1.0 |  | 1st July 2024 |  |  |  |  |
| Amendment approval by Hospital for Tropical Diseases |  |  |  |  |  |  | V2.0 |  | 26th June 2025 |  |  |  |  |
| Initial approval by National Hospital for Tropical Diseases |  |  |  |  |  |  | V2.1 |  | 1st August 2025 |  |  |  |  |
| Initial approval by Cho Ray Hospital |  |  |  |  |  |  | V2.2 |  | 8th September 2025 |  |  |  |  |
| Amendment approval by OxTREC 522-24 |  |  |  |  |  |  | V2.0 |  | 3rd November 2025 |  |  |  |  |

| Event |  |  |  |  | HTD | Cho Ray Hospital | NHTD |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Site initiation |  |  |  |  | 01- | 13 | 05 |
| First Subject In |  |  |  |  |  | 17 | 06- |
| Plan End recruitment |  |  |  |  | 2027 |  | 30- |
| Total recruitment durations |  |  |  |  | months | months | months |
| Target recruited patients per month |  |  |  |  | atients/ month | / month | nts/ month |
| Target recruited patients as of Nov-25 |  |  |  |  |  |  |  |
| Cumulative Patient (%/target) |  |  |  |  |  |  |  |
| Cumulative Contact |  |  |  |  |  |  |  |

I

TMG REPORT

Document code: TM-CTU-003 Section : CTU

Version: 4.0

ucru

Effective: 06JAN22

Table 1: Recruitment at hospital study sites over the last six months – as of 28Nov2025

HTD

Cho Ray Hospital (from 13Oct2025)

NHTD

(from 01.1ul2024)

(from 05Nov2025)

PATIENT

CONTACT

PATIENT

CONTACT

PATIENT

CONTACT

| Jul24 – Jun25 |  |  | - | - | - | - |
| --- | --- | --- | --- | --- | --- | --- |
| Jul-25 |  |  | - | - | - | - |
| Aug-25 |  |  | - | - | - | - |
| Sep-25 |  |  | - | - | - | - |
| Oct-25 |  |  |  |  | - | - |
| Nov-25 |  |  |  |  |  |  |
| TOTAL |  |  |  |  |  |  |

Table 2: Screening and Enrolment figures (01JUL24 – 28NOV25)

HTD

Cho Ray Hospital (from 13Oct2025)

NHTD

(from 01.1ul2024)

(from 05Nov2025)

PATIENT

CONTACT

PATIENT

CONTACT

PATIENT

CONTACT

Page 2 of 5

TM-CTU-003 TEMPLATE TMG REPORT V4.06JAN22

Note: This is a controlled document

N/A

N/A

N/A

N/A

N/A

□

| Screened |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Enrolled |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Randomised |  |  |  |  |  |  |  | N/A | N | N/A | N/A | N/A | N |
| Ineligible |  |  |  |  |  |  |  |  |  |  |  |  | 4 |
| Missed |  |  |  |  |  |  |  |  | 0 | 8 | 0 | 0 | 0 |
| Declined |  |  |  |  |  |  |  |  | 9 | 3 | 6 | 0 | 0 |
| Death |  |  |  |  |  |  |  | 11 | 0 | 3 | 0 | 1 | 0 |
| Withdrawn |  |  |  |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |
| Lost to Follow Up |  |  |  |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |
| Unblinded |  |  |  |  |  |  |  | N/A |  |  |  |  |  |

I

TMG REPORT

Document code: TM-CTU-003 Section : CTU

Version: 4.0

ucru

Effective: 06JAN22

Table 3: Details for missed/declined consent:

Table 4: Cumulative Figures by Site as of 28-Nov-2025

HTD

Cho Ray Hospital ()

NHTD

(

(from

PATIENT

CONTACT

PATIENT

CONTACT

PATIENT

CONTACT

5. Sample Management:

Table 5: Patient sampling and follow-up (1JUL24-28NOV25)

PATIENT

CONTACT

Schedule

Total

patient

Blood

sampling

Total

contact

Blood

sampling

|  |  | 1 |  |  |
| --- | --- | --- | --- | --- |
| Sampling_Visit 1 (Day 1) |  |  |  |  |
| Sampling_Visit 2 (Day 10) |  |  | - | - |
| Sampling_Visit 3 (Day 28) | 9 | 6 | 6 | - |
| Sampling_Visit 4 (Day 90) |  | - |  | - |
|  |  | - | - | - |

Page 3 of 5

TM-CTU-003 TEMPLATE TMG REPORT V4.06JAN22

Note: This is a controlled document

Enrolled

Discharged

□

| Missed/Declined Reason |  |  |  |  |  | No. of Patient | No. of Contact |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Participant does not want to participate in research |  |  |  |  |  |  |  |
| Not enough time/ too busy to commit |  |  |  |  |  |  |  |
| Not able to get informed consent |  |  |  |  |  |  |  |
| Dr/RN too busy to screen participant properly |  |  |  |  |  |  | 0 |
| Total |  |  |  |  |  |  |  |

| Cumulative Recruitment |  |  |  |  |  |  |  | 4 | 6 | 1 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Recruitment Target |  |  |  |  |  | - |  | - |  | - |
| % Target Completion |  |  |  |  |  | - |  | - |  | - |
| Total Death |  |  |  |  | 11 | 0 | 3 | 0 | 1 | 0 |
| Total Withdrawn |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |
| Total Loss to Follow Up |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |
| Total Unblinded (or N/A) |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A |

I

TMG REPORT

Document code: TM-CTU-003 Section : CTU

Version: 4.0

ucru

Effective: 06JAN22

Table 7: No. of K. pneumoniae isolated from throat swab & stool/rectal swab samples of Patients and  Close contacts (1Jul2024 – 28Nov2025)

Study

site

Subject

No. of

participant

Clinical

Kp.

Throat swab*

Stool/Rectal swab*

Day

Day

Day

Day

Day

Day

Day

Day

1

10

28

90

1

10

28

90

HTD

|  |  |  |  |  |  | 0/2 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | - |  | - | 0/6 | 2/2 |  | - |  |  |
| Complicated cases |  |  | - | - | - | - | - | - | - | - |
|  |  |  |  |  | - | - |  | 3 | - | - |
|  |  | - |  | - | - | - | 4 | - | - | - |
|  |  | 6 | 6 | 0/5 | - | - |  |  | - | - |
|  | 1 | - | 0/1 | - | - | - | 0/1 | - | - | - |

Cho

Ray

NHTD

* K. pneumoniae positive sample/Total collected samples

6. Site Management

- Completeness and return of CRFs: all clinical information on CRFs should be completed within 7 days

of patient discharge.

- Postpone recruitment at the NHTD site in December 2025, continue to follow-up with already

recruited participants.

7. Data Management

Data Entry Method: Single data entry

Table 8: Data Entry – NOV25

HTD

Cho Ray Hospital

NHTD

Patient

Contact

Patient

Contact

Patient

Contact

Page 4 of 5

TM-CTU-003 TEMPLATE TMG REPORT V4.06JAN22

Note: This is a controlled document

Patient

Contact

Patient

Contact

Patient

Contact

□

| CRFs Received from site |  |  |  |  |  |  |  | 0 | 0 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| CRFs Entered in CliRes |  |  |  |  |  |  |  | 0 | 0 |
| CRFs Remaining |  |  |  |  |  |  | 0 |  | 1 |

I

TMG REPORT

Document code: TM-CTU-003 Section : CTU

Version: 4.0

ucru

Effective: 06JAN22

Table 9: Total Data Management Figures

8. SAE/SUSARs

N/A.

9. Protocol Violations/Deviations

Table 10: Reported Protocol Deviations and Violations for NOV25 None since JUL-24

Subject

No.

Site

Date of

Protocol

Deviation

Describe the protocol Deviation / Violation

Comments / Corrective Preventative

Is this a

protocol

violation?

Action

10. AOB

No.

Page 5 of 5

TM-CTU-003 TEMPLATE TMG REPORT V4.06JAN22

Note: This is a controlled document

□

| Total Expected CRFs (sample size x No of forms) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Total Received CRF |  |  |  |  |
| Total Entered CRF |  |  |  |  |
| % Completion |  |  |  |  |